## Product Backlog
| SPRINT #1 BACKLOG |  | PROJECT: NEIGHBOURHOOD DOCTORS |  | TEAM: GR12 BIN CHICKENS
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | Build doctor verification with accreditation number | 1.1 | Make the database with registration table | Luke, Ash | X
1 | Build doctor verification with accreditation number | 1.2 | Create GUI for landing page (see wireframe) | Luke, Ash | X
1 | Build doctor verification with accreditation number | 1.3 | Verify that input is 'legal'/satisfies business requirements (has accreditation number) | Luke, Ash | X
1 | Build doctor verification with accreditation number | 1.4 | Verify that doctor is not already in the database | Luke, Ash | X
1 | Build doctor verification with accreditation number | 1.5 | Create new doctor row in the database if a) legal and b) not already registered (added as 'active' but pending approval) | Luke, Ash | X
1 | Build doctor verification with accreditation number | 1.6 | Redirect to 'waiting approval' page | Luke, Ash | X
2 | Build admin verification of doctor verification number | 2.1 | Create GUI for login page | Luke, Ash | X
2 | Build admin verification of doctor verification number | 2.2 | Create GUI for doctor verification page | Luke, Ash | X
2 | Build admin verification of doctor verification number | 2.3 | Fetch list of all unverified doctors from database (into doctor objects) | Luke, Ash | X
2 | Build admin verification of doctor verification number | 2.4 | Display list of all unverified doctors with approval buttons beside | Luke, Ash | X
2 | Build admin verification of doctor verification number | 2.5 | When approved, update doctor record within database | Luke, Ash | X
2 | Build admin verification of doctor verification number | 2.6 | Make the database with registration table | Luke, Ash | X
3 | Build sign up to ND health for patients. | 3.1 | Create GUI for landing page (see wireframe) | Joseph, Abdul | X
3 | Build sign up to ND health for patients. | 3.2 | Verify that input is 'legal'/satisfies business requirements | Joseph, Abdul | X
3 | Build sign up to ND health for patients. | 3.3 | Verify that Patient is not already in the database | Joseph, Abdul | X
3 | Build sign up to ND health for patients. | 3.4 | Create new patient row in the database if a) legal and b) not already registered. | Joseph, Abdul | X
3 | Build sign up to ND health for patients. | 3.5 | Create patient profile object and assign information for the patient that is registering | Joseph, Abdul | X
3 | Build sign up to ND health for patients. | 3.6 | Redirect to the patient home page -> make home page using wireframe as a guide. | Joseph, Abdul | X
4 | Build patient profile | 4.1 | Create the health information table(s) in the database | Amy | X
4 | Build patient profile | 4.2 | Create health information GUI page | Amy | X
4 | Build patient profile | 4.3 | Display current patient information (stored in patient object) in the GUI. | Amy | X
4 | Build patient profile | 4.4 | Save patient information to the database row after changes or additions have been made (also handed back to patient object) | Amy | X
5 | Build sign up to ND health for doctor. | 5.1 | Make the database with registration table. | Joseph, Abdul | X
5 | Build sign up to ND health for doctor. | 5.2 | Create GUI for landing page (see wireframe) | Joseph, Abdul | X
5 | Build sign up to ND health for doctor. | 5.3 | Verify that input is 'legal'/satisfies business requirements | Joseph, Abdul | X
5 | Build sign up to ND health for doctor. | 5.4 | Verify that doctor is not already in the database | Joseph, Abdul | X
5 | Build sign up to ND health for doctor. | 5.5 | Create new doctor row in the database if a) legal and b) not already registered (added as 'active' but pending approval) | Joseph, Abdul | X
5 | Build sign up to ND health for doctor. | 5.6 | Redirect to 'waiting approval' page | Joseph, Abdul | X
6 | Build API functionality for registration | 6.1 | Setup API gateway | Amy | X
6 | Build API functionality for registration | 6.2 | Make the database with registration table. | Amy | X
6 | Build API functionality for registration | 6.3 | Create GUI for landing page (see wireframe) | Amy | X
6 | Build API functionality for registration | 6.4 | Verify that input is 'legal'/satisfies business requirements | Amy | X
6 | Build API functionality for registration | 6.5 | Verify that Patient is not already in the database | Amy | X
6 | Build API functionality for registration | 6.6 | Create new patient/doctor row in the database if a) legal and b) not already registered | Amy | X
6 | Build API functionality for registration | 6.7 | Create API endpoint (POST method) | Amy | X

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Build doctor verification with accreditation number | #N/A | #N/A | #N/A | #N/A | #N/A
2 | Build doctor verification with accreditation number | #N/A | #N/A | #N/A | #N/A | #N/A
3 | Build doctor verification with accreditation number | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Build doctor verification with accreditation number | #N/A | #N/A | #N/A | #N/A | #N/A
7 | Build doctor verification with accreditation number | #N/A | #N/A | #N/A | #N/A | #N/A
8 | Build doctor verification with accreditation number | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Build admin verification of doctor verification number | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Build admin verification of doctor verification number | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Build admin verification of doctor verification number | #N/A | #N/A | #N/A | #N/A | #N/A
12 | Build admin verification of doctor verification number | #N/A | #N/A | #N/A | #N/A | #N/A
13 | Build admin verification of doctor verification number | #N/A | #N/A | #N/A | #N/A | #N/A
14 | Build sign up to ND health for patients. | #N/A | #N/A | #N/A | #N/A | #N/A
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | Build sign up to ND health for patients. | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Build sign up to ND health for patients. | #N/A | #N/A | #N/A | #N/A | #N/A
18 | Build sign up to ND health for patients. | #N/A | #N/A | #N/A | #N/A | #N/A
19 | Build sign up to ND health for patients. | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Build sign up to ND health for patients. | #N/A | #N/A | #N/A | #N/A | #N/A
21 | Build patient profile | #N/A | #N/A | #N/A | #N/A | #N/A
22 | Build patient profile | #N/A | #N/A | #N/A | #N/A | #N/A
23 | Build patient profile | #N/A | #N/A | #N/A | #N/A | #N/A
24 | Build patient profile | #N/A | #N/A | #N/A | #N/A | #N/A
25 | Build sign up to ND health for doctor. | #N/A | #N/A | #N/A | #N/A | #N/A